## Sheet1
Activity No. | Activity Name | Duration (days) | Start Date | End Date | Assigned Resources | Dependencies
1 | Project Management & Initiation | 10 | 2026-03-02 | 2026-03-13 | Project Manager
1.1 | Project Chartering | 3 | 2026-03-02 | 2026-03-04 | PM, Project Sponsor
1.2 | Stakeholder Setup | 4 | 2026-03-05 | 2026-03-10 | PM, 12 Regional Leads | 1.1
1.3 | Risk Planning | 3 | 2026-03-11 | 2026-03-13 | PM | 1.2
M1 | Milestone: Charter Approved | 0 | 2026-03-13 | 2026-03-13 | - | 1.3
2 | Requirements Gathering & Analysis | 10 | 2026-03-16 | 2026-03-27 | Business Analyst (BA) | M1
2.1 | Needs Discovery (Workshops) | 5 | 2026-03-16 | 2026-03-20 | BA, Regional Leads | M1
2.2 | Systems & Security Audit | 3 | 2026-03-23 | 2026-03-25 | Security Expert, IT Team | 2.1
2.3 | BRD Development | 2 | 2026-03-26 | 2026-03-27 | BA, Project Manager | 2.2
M2 | Milestone: Requirements Baseline | 0 | 2026-03-27 | 2026-03-27 | - | 2.3
3 | Vendor Selection & Procurement | 7 | 2026-03-30 | 2026-04-07 | PM, Legal Counsel | M2
3.1 | RFP Process | 3 | 2026-03-30 | 2026-04-01 | PM, IT Department | M2
3.2 | Solution Evaluation | 3 | 2026-04-02 | 2026-04-06 | PM, BA | 3.1
3.3 | Contract Finalization | 1 | 2026-04-07 | 2026-04-07 | Legal, PM, Vendor | 3.2
M3 | Milestone: CRM Vendor Selected | 0 | 2026-04-07 | 2026-04-07 | - | 3.3
4 | Data Migration & Quality Control | 12 | 2026-04-08 | 2026-04-23 | (DS) | M3
4.1 | Data Audit & Cleanup | 4 | 2026-04-08 | 2026-04-13 |  | M3
4.2 | Schema Mapping | 3 | 2026-04-14 | 2026-04-16 | Vendor | 4.1
4.3 | Migration Execution & Verify | 5 | 2026-04-17 | 2026-04-23 | IT Team | 4.2
M4 | Milestone: Data Verified | 0 | 2026-04-23 | 2026-04-23 | - | 4.3
5 | System Setup & UAT | 6 | 2026-04-24 | 2026-05-01 | Vendor, QA Team | M4
5.1 | Configuration & Governance | 2 | 2026-04-24 | 2026-04-27 | Vendor, Project Manager | M4
5.2 | Reporting & Analytics | 2 | 2026-04-28 | 2026-04-29 | BA | 5.1
5.3 | UAT Execution | 2 | 2026-04-30 | 2026-05-01 | Test Users, QA Team | 5.2
M5 | Milestone: System Ready | 0 | 2026-05-01 | 2026-05-01 | - | 5.3
6 | Training & Change Management | 3 | 2026-05-04 | 2026-05-06 | Trainer, Users | M5
6.1 | Material Development | 1.5 | 2026-05-04 | 2026-05-05 | Trainer | M5
6.2 | Training Delivery | 1.5 | 2026-05-05 | 2026-05-06 | Trainer, Regional Leads | 6.1
7 | Deployment & Closure | 1.5 | 2026-05-04 | 2026-05-05 | IT Team, PM | M5
7.1 | System Go-Live | 0.5 | 2026-05-04 | 2026-05-04 | IT Team, Vendor | M5
7.2 | Hypercare Support | 0.5 | 2026-05-05 | 2026-05-05 | IT Support Team | 7.1
7.3 | Project Closure & Report | 0.5 | 2026-05-05 | 2026-05-05 | Project Manager, BA | 7.2