Team 6: Bhavisha Ahuja, Jamil Gasali, Yunjae Jung, Jasmine Vazquez, Nam Nguyen

| ## Risk Register |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Risk ID | Risk Description | Likelihood of Risk Occurring | Impact if Risk Occurs | Severity (Rating Based on Impact & Likelihood) | Owner (Person Who will Manage the Risk) | Mitigating Action |
| R1 | Legacy data migration causes data loss or corrupted records when moving to the new CRM | Medium | High | High | Data Owners or Database Admin for Legacy System | Run data cleanup first, do a test migration, back up data, and validate samples before final cutover. |
| R2 | Poor legacy data quality reduces accuracy and reporting in the new CRM | High | High | High | Data Owners or Database Admin for Legacy System | Set data standards, prioritize cleaning key donor/volunteer fields, and approve cleanup rules before migration. |
| R3 | CRM vendor delay or limited capacity pushes configuration/testing and delays go live | Medium | High | High | CRM Vendor Implementation Team | Confirm milestones in writing, hold weekly check-ins, escalate early, and keep a backup plan for schedule adjustments |
| R4 | Staff resistance to change leads to low adoption and weak usage after go live | Medium | High | High | Training Lead or Change Champion Group | Use office champions, communicate benefits early, keep training simple, and provide support during the first month after go live |
| R5 | Training completion is below the 80 percent target within one month after go live | Medium | Medium | Medium | Training Lead or Change Champion Group | Offer multiple sessions, track attendance by office, provide quick guides, and schedule follow up office hours |
| R6 | Requirements change after discovery, causing scope creep and rework | Medium | Medium | Medium | Executive Director | Require approval for changes, and evaluate impacts to time and budget before accepting changes |
| R7 | Reporting needs are not met because report issues show up late in UAT/testing | Medium | Medium | Medium | Fundraising Staff | Define key reports early, build a quick prototype, test reports with users early, and fix gaps before go live |
| R8 | Permissions are set up incorrectly, causing privacy risk or blocking staff from needed access | Low | High | Medium | IT Support or Technical Lead | Define roles early, test with sample accounts, and have IT review permissions and security before go live |
| R9 | Key staff across 12 offices are not available for workshops, testing, or training on time | High | Medium | High | Regional Office Directors | Schedule early, keep sessions short, allow async feedback, and assign one office champion per location to represent needs |
| R10 | Go live causes disruption to daily operations due to downtime or unresolved issues | Low | Medium | Low | Project Sponsor | Plan cutover during low activity periods, communicate downtime early, and run a 30-day stabilization period with fast issue tracking |