Course Project Status Report #3

Team 6 | HelpingHands CRM Implementation Planning

Reporting Period: March 24 – April 14, 2026

Team Members: Bhavisha Ahuja, Jamil Gasali, Yunjae Jung, Jasmine Vazquez, Nam Nguyen

Question 1: What have we accomplished since the last reporting period?

- We held our second team meeting this week to check in on progress and divide up the remaining work. Bhavisha and Ansh are handling the WBS, Yunjae is working on the project schedule, Nam is taking on the stakeholder register, and Jasmine and Jamil are collaborating on the risk register.

- The team agreed on an internal deadline of May 1st to have all individual drafts ready. This gives us a few days to review each other's work, make any changes based on instructor feedback, and put together the full project management plan over the weekend before the May 5th submission.

- Each team member also reviewed the full list of remaining deliverables (#4 through #9) to make sure everyone is aligned on what is expected, including the individual personal reflection that each of us needs to write separately.

Question 2: What do we intend to accomplish before the end of this reporting period?

- Submit this status report by the April 29th deadline and continue making steady progress on our individually assigned deliverables throughout the rest of this month.

- Have all draft components completed and shared with the team by May 1st so we have time to review, refine, and incorporate any feedback from the instructor before assembling the final submission.

- Bring everything together over the weekend of May 3rd and 4th to produce the final project management plan and ensure all deliverables are polished and ready to submit by May 5th.

Question 3: What challenges or obstacles have or could be encountered?

- The end of the semester is a busy time for everyone on the team, with final exams, other deadlines, and graduation preparations all happening at once. We are doing our best to stay ahead of the work so nothing gets rushed at the last minute.

- Our May 1st internal deadline is fairly tight, and if any one piece of the work runs behind it could create pressure when it comes time to assemble and finalize Deliverable #4 as a group over the weekend.

- Coordinating asynchronously across five team members with different schedules has been an ongoing challenge throughout the project. We are managing it through shared documents and regular group communication, but it does require everyone to stay proactive and responsive.